## Duration
Task Name | Most Probable Duration (days) | Optimistic Duration | Pessimistic Duration | Expected Time |  | Variance
Insurance | 0 |  |  |  | 0 | 0
Insurance Broker | 0 |  |  |  | 0 | 0
Negotiate with Insurance broker | 5 | 3 | 7 | 5 | 0.66667 | 0.44444
Find Insurance broker | 2 | 1 | 3 | 2 | 0.33333 | 0.11111
Storage Space Insurance | 0 |  |  |  | 0 | 0
Define terms needed for simulation of a Storage Space Insurance | 2 | 0.5 | 5 | 2.25 | 0.75 | 0.5625
Evaluate and select a plan from the broker's simulations of a Storage Space Insurance | 2 | 0.5 | 2 | 1.75 | 0.25 | 0.0625
Equipment Insurance | 0 |  |  |  | 0 | 0
Define terms needed for simulation of a Equipment Insurance | 7 | 4 | 10 | 7 | 1 | 1
Evaluate and select a plan from the broker's simulations of a Equipment Insurance | 1 | 0.5 | 3 | 1.25 | 0.41667 | 0.17361
Employees Insurance | 0 |  |  |  | 0 | 0
Define terms needed for simulation of a Employees Insurance | 1 | 0.5 | 3 | 1.25 | 0.41667 | 0.17361
Evaluate and select a plan from the broker's simulations of a Employees Insurance | 1 | 0.5 | 3 | 1.25 | 0.41667 | 0.17361
Equipment | 0 |  |  |  | 0 | 0
Equipment Provider | 0 |  |  |  | 0 | 0
Search for an Equipment Provider | 1 | 0.5 | 3 | 1.25 | 0.41667 | 0.17361
Negotiate Contracts with a Equipment Provider | 6 | 3 | 12 | 6.5 | 1.5 | 2.25
Transport Equipment to Storage | 4 | 1 | 7 | 4 | 1 | 1
Equipment Transport | 0 |  |  |  | 0 | 0
Search and Evaluate Equipment Transport Services | 1 | 0.5 | 3 | 1.25 | 0.41667 | 0.17361
Negotiate Contracts with a Equipment Transport Service | 7 | 1 | 10 | 6.5 | 1.5 | 2.25
Equipment Maintenance | 0 |  |  |  | 0 | 0
Search and Evaluate Equipment Maintenance Services | 1 | 0.5 | 3 | 1.25 | 0.41667 | 0.17361
Negotiate Contracts with a Equipment Maintenance | 7 | 4 | 10 | 7 | 1 | 1
Platform | 0 |  |  |  | 0 | 0
Website Development | 0 |  |  |  | 0 | 0
Search for a Web Development Team | 9 | 6 | 15 | 9.5 | 1.5 | 2.25
Negotiate Contracts with a Web Development Team | 6 | 5 | 10 | 6.5 | 0.83333 | 0.69444
Requirement Definition with the Web Development Team | 5 | 3 | 7 | 5 | 0.66667 | 0.44444
Developing the Platform | 120 | 110 | 130 | 120 | 3.3333 | 11.1111
Website Development deliverables evaluation | 11 | 7 | 15 | 11 | 1.3333 | 1.7778
Hosting Service | 0 |  |  |  | 0 | 0
Find a good hosting Service plan | 4 | 2 | 9 | 4.5 | 1.1667 | 1.3611
Negotiate contract with the Hosting service plan | 7 | 4 | 10 | 7 | 1 | 1
Storage | 0 |  |  |  | 0 | 0
Search for a storage rental Service | 1 | 0.5 | 3 | 1.25 | 0.41667 | 0.17361
Negotiate storage rental contract | 7 | 4 | 10 | 7 | 1 | 1
Prepare storage space | 14 | 10 | 18 | 14 | 1.3333 | 1.7778
Storage Space maintenance | 17 | 12 | 22 | 17 | 1.6667 | 2.7778
Finances and Human Storage | 0 |  |  |  | 0 | 0
Search for a Finance and Human resources team | 4 | 2 | 9 | 4.5 | 1.1667 | 1.3611
Negotiate contract with the Finances and Human resources team | 7 | 4 | 10 | 7 | 1 | 1
Provide the Finance and Human resources team data | 15 | 2 | 7 | 11.5 | 0.83333 | 0.69444
Marketing | 0 |  |  |  | 0 | 0
Advertisement | 0 |  |  |  | 0 | 0
Create Adds | 30 | 24 | 36 | 30 | 2 | 4
Manage Social Network Pages | 30 | 26 | 34 | 30 | 1.3333 | 1.7778
Buy spaces for advertisement | 1 | 0.5 | 3 | 1.25 | 0.41667 | 0.17361
Create logos and mottos | 7 | 4 | 10 | 7 | 1 | 1
Establish the company's Orientation | 0 |  |  |  | 0 | 0
Create vision | 3 | 1 | 5 | 3 | 0.66667 | 0.44444
Create mission | 3 | 1 | 5 | 3 | 0.66667 | 0.44444
Create values | 3 | 1 | 5 | 3 | 0.66667 | 0.44444
Lawyer
Contract Lawyer | 2 | 0.5 | 5 | 2.25 | 0.75 | 0.5625
Search for a Lawyer | 5 | 2 | 8 | 5 | 1 | 1
Investors | 0 |  |  |  | 0 | 0
Search for investors | 30 | 26 | 34 | 30 | 1.3333 | 1.7778
Negotiate investment plans | 7 | 4 | 10 | 7 | 1 | 1
Project Management | 0 |  |  |  | 0 | 0
Financial Management | 17 | 15 | 21 | 17.3333 | 1 | 1
Risk Management | 0 |  |  |  | 0 | 0
Risk Evaluation | 18 | 16 | 22 | 18.3333 | 1 | 1
Make risk reports | 18 | 16 | 22 | 18.3333 | 1 | 1
Quality Assurance | 0 |  |  |  | 0 | 0
Make test report | 7 | 5 | 12 | 7.5 | 1.1667 | 1.3611
Make marketing report | 6 | 4 | 8 | 6 | 0.66667 | 0.44444
Make deliverable reports | 19 | 17 | 25 | 19.6667 | 1.3333 | 1.7778
Observation Phase | 131 | 131 | 131 | 131 | 0 | 0
Conclusion Phase | 64 | 64 | 64 | 64 | 0 | 0
Total | 676 |  |  | 678.9167 |  | 56.3542
critical path: 58 - 59 - 56 - 27- 28 - 29 - 30 - 69 - 70 | 374 |  |  | 375.25 |  | 17.8403
Total
|  |  | Z | -0.38853
|  |  | P(-Z) | 0.34881
|  |  | 1 - P(-Z) | 0.65119
|  |  | D2 | 1
|  |  | D3 | 1
[5 empty] | Estimated time | 377
Critical Path
[5 empty] | Z | 0.41432
[5 empty] | P(-Z) | 0.66068
[5 empty] | D2 | 1
[5 empty] | D3 | 1